**2.2 Research project description template**

***EURIZON FELLOWSHIP PROGRAMME***

***“Remote Research Grants”***

**Valid applications need to be submitted through the website:** [**https://indico.desy.de/event/38700/**](https://indico.desy.de/event/38700/) **by the Principal Investigator of the Ukrainian team before May 8th 2023 at 12:00 Pm (noon) CEST time. Before applying please read carefully the Terms of Reference (ToR).**

|  |
| --- |
| **Title[[1]](#footnote-2)of the research project:** *(max 30 words)*  **Machine learning-based defect engineering in silicon structures for thermal management and solar cells applications**  **Як варіант**  **Machine learning-based thermal management and defect evaluation in silicon structure for photovoltaics and ???? application** |

submitted by

***PRINCIPAL INVESTIGATOR (PI)[[2]](#footnote-3):***

|  |  |
| --- | --- |
| *First name and Family name (English)* |  |

***Please note that the limit in the number of words per each section of this application form constitutes one of the eligibility criteria****, so make sure that all requirements are respected. The template provided must not be modified and the formatting must be kept. All possible tables and pictures must be clearly readable.*

*All fields marked with\* are mandatory. Other fields are optional.*

*This template is part of the application package. It must be filled according to the instructions, signed by all team members, and upload it as pdf file*

***Table of Contents:***

*2.2 Research project description......………………………….…………………………………………………………..2*

*2.3 Collaboration with the European partners, impact, dissemination......................................2 2.4 Research team description and financial plan....………………………………………………………….…..3*

*2.5 Signatures.............................................................................................................................6*

**Please note that the limit in the number of words per each section of this application form constitutes one of the eligibility criteria.**

**2.2 Research project´s full description\*** *(Max 1200 words)*

Please describe the objectives of the research, and whenever possible the methodology to be used, the instrumentation needed (if any), the implementation and timeline.

|  |
| --- |
| **Introduction:** In the last few years, materials Informatics (MI) has become one of the leading scientific paradigms, transforming the material and device development, characterization, and investigation fields by merging material property calculations/measurements with the computational power of informatics algorithms. Machine learning (ML) techniques have proven very successful within the MI, particularly in scenarios where conventional algorithm-based solutions are not readily apparent.  One of the promising directions for the ML application is related to predicting thermal transport in solids [1]. Proverbially, designing materials with superb thermal properties is of critical importance in a lot of technological applications. Тут би речення про важливість термо-менеджменту кремнієвих структур. Specifically, for the efficient conversion from thermal energy to electrical energy, materials must have relatively low thermal conductivity values. On the other hand, materials with high thermal conductivity are promising heat channels to dissipate heat from hot-spot. Therefore, the accurate evaluation of thermal conductivity is of great scientific and practical interest in many fields. So far, many approaches have been proposed to control the thermal transport in materials, such as the introduction of impurity scattering, surface roughness, alloy and porous structures. Recently, the possibility of successfully solving thermal management problems by coupling molecular dynamics and machine learning has been demonstrated [2], as well as the applicability of MI methods to describe the thermal properties of porous materials [3]. One of the project's tasks is molecular dynamics-based machine learning thermal management of silicon and silicon-germanium systems with varying porosity and defects.  The other project’s part deals with impurity evaluation in silicon solar cells (SSCs). One of the most crucial technologies for achieving a society free of carbon emissions is solar photovoltaics (PV). It is an effective and renewable energy source, but various defects limit solar cells performance and reliability. Therefore, non-destructive methods aimed at estimating the concentration of recombination-active defects in PV structures are crucial from an applied point of view. Numerous methods have been developed to address this issue, but most involve either pre-treatment of the samples or specialized equipment. On the other hand, the measurement of current-voltage characteristics (IVCs) is a widely accepted and straightforward method for determining the parameters of photovoltaic conversion in SCs. The ways for characterizing defects from IVC measurements and Bayesian parameter estimation [4], or differential coefficients [5], were demonstrated previously. However, these approaches are too complex for practical use. The project aims to develop a machine learning-oriented express method for IVC-based impurity determination, which is highly desirable and promising for widespread use. Lately, the ML's possibility of silicon defect characterization was shown using lifetime curves [6] or ideality factor [7]. Our approach is based on using standard photovoltaic parameters as factors sensitive to the recombination centers and makes it possible to reduce the requirements for IVC measurement.  **Objective:** The primary objective of this research project is to develop a machine learning-based approach to defects evaluation in silicon structures that can enhance the reliability of solar modules and thermal management applications. Specifically, we aim to achieve the following objectives:   * Develop a machine learning (ML) model to predict the impact of defects on the performance of silicon structures for solar cells and thermal management applications. * Use the machine learning model to design and engineer defects that can enhance the performance of silicon structures. * Develop a machine learning based approach to extracting defect concentration from current-voltage characteristic of solar cell. * Synthesis of a limited series of porous silicon structures and structures based on a silicon-germanium alloy, experimental investigations of their thermal properties using photoacoustic methods, and experimental verification of theoretical models.   **Methodology:** The proposed research project will involve the following steps:  *Step 1:* Data Collection and Preparation: We will collect data on the impact of different types of defects on the performance of silicon structures for solar cells and thermal management applications. The data will be obtained through experiments and simulations. The data will be pre-processed to remove noise and outliers, and feature engineering techniques will be used to extract meaningful features. The simulations of thermal transport in silicon structures will be performed using molecular dynamics method in the LAMMPS package and/or Anharmonic Lattice Dynamics (using the kALDo software). The calculation of the current-voltage characteristics of silicon structures will be carried out using the SCAPS software. A total of 100,000 IVCs are estimated to be required to ensure high-quality ML training.  *Step 2:* Machine Learning Model Development: We will develop a machine learning models to predict the impact of defects on the performance of silicon structures, as well as ML models to predict the concentration of defect (iron, for example) based on the photoelectric parameters of solar cells (short-circuit current, open-circuit voltage, efficiency, and fill factor) and the set of IV curves obtained after light-induced dissociation of FeB pairs. The model will be trained and tuned on the pre-processed data collected in Step 1. To develop the model, we will explore different machine learning algorithms, including dense neural networks (DNN), random forest (RF), convolutional neural networks (CNNs). In the case of CNN, the fine-tuning of vision models (AlexNet or VGG network) will be used as well. The ML algorithms will be implemented using the TensorFlow platform, specifically the high-level Keras API.  *Step 3:* Defect Engineering: We will use the developed machine learning model to engineer defects in silicon structures that can enhance their performance. We will use an optimization algorithm, such as EBLSHADE or IJAVA, to search for the optimal defect parameters that can maximize the performance of the silicon structure. The defect parameters will be constrained by physical and material properties of the silicon structure.  *Step 4:* Fabrication, Testing and Evaluation: The porous silicon and SiGe alloy structures will be fabricated using standard processing techniques. *(реально створити сонячні елементи я не бачу можливості – є готові, на яких можна тестувати методи оцінки дефектів)* The thermal transport properties of the fabricated structures will be evaluated using experiments and simulations. We will compare the performance of the synthesized structures with that of the original structures to evaluate the effectiveness of the defect engineering approach. The ability of the developed ML method of defect evaluation will be tested on actual silicon solar cells.  **Expected Results:** The proposed research project is expected to result in the following outcomes:   1. A machine learning model to predict the impact of defects on the performance of silicon structures for solar cells and thermal management applications. 2. A machine learning model to evaluate defect concentration in solar cells by standard photovoltaic parameters. 3. An approach to engineer defects in silicon structures that can enhance their thermoelectric performance. 4. ~~Fabricated silicon structures with engineered defects that demonstrate enhanced performance.~~ Fabricated limited series of silicon structures including porous Si and SiGe alloy samples for experimental validation of the modeling results.  A better understanding of the role of defects in silicon structures for solar cells and thermal management applications.   **Significance and Impact:** The proposed research project has significant implications for the development of efficient, reliability, and effective solar photovoltaic modules and thermal management systems. By using machine learning-based defect engineering techniques, we can design, characterize, and engineer silicon structures that can enhance their performance. This can lead to the development of more efficient solar cells and thermal management systems, which can have a significant impact on the energy sector. In addition, the proposed research project can contribute to the development of new materials and technologies for other applications where silicon structures are used. |

**2.3 COLLABORATION WITH THE EUROPEAN PARTNERS, IMPACT, DISSEMINATION**

**2.3.1 Description of the collaboration with the European partner(s)[[3]](#footnote-4)\*.** *(Max 500 words)*

Please describe the expected role of the European partner and the scope of the collaboration.

*The repartition of work can also be very different, with the Ukrainian team performing most of the tasks, but it is important to explain the role of the European Partners (e.g. joint analysis, support, monitoring, dissemination, etc.).*

|  |
| --- |
| *Please indicate what kind of collaboration is foreseen and if there are specific contributions and/or external funding available for the actions requested (e.g. European partner willing to perform an experiment at their facilities and/or to host and contribute to travel and accommodation expenses of Ukrainian team members).* |

**2.3.2 Expected outcomes of the research project\*.** *(Max 300 words)*

Please highlight the possible positive impact of your research project. Please also highlight if the project could (i) support the operations and/or reconstruction and/or long-term sustainability of Ukrainian RIs and/or (ii) boost possible future collaboration and partnership opportunities with European Research Institutes.

|  |
| --- |
| The expected outcomes of the project could be:   1. Development of advanced algorithms: The project could result in the development of advanced machine learning algorithms that could be used for thermal management and defect evaluation in silicon structures. These algorithms could help in improving the performance and efficiency of photovoltaic and thermoelectric devices. This is particularly important because the restoration of Ukraine's energy system, which was significantly damaged by Russian’s aggression, will largely depend on renewable technologies, such as photovoltaics. 2. Enhanced device performance: The research could lead to the identification of defects that could affect the performance of photovoltaic and thermoelectric devices. This could result in the production of more efficient and reliable devices. 3. Creating of data collection: The big data array, obtained through experiments and simulations, will be in open access and may be used by other researchers. 4. Improved manufacturing processes: The machine learning algorithms developed in this project could be used to improve the manufacturing processes of photovoltaic and thermoelectric devices. This could lead to the production of high-quality devices at lower costs. 5. Positive impact on the environment: The use of photovoltaic and thermoelectric devices could reduce the dependence on fossil fuels, leading to a positive impact on the environment. The improved efficiency and reliability of these devices could further promote their use.   Regarding the project's potential impact on Ukrainian RIs and European research institutes, it could:  (i) The development of advanced algorithms and improved manufacturing processes could have a positive impact on the sustainability and competitiveness of Ukrainian RIs. The project could help in the development of new technologies and processes that could be used to improve the performance of photovoltaic and thermoelectric devices in Ukraine.  (ii) The development of advanced machine learning algorithms and improved manufacturing processes could attract the attention of European research institutes, leading to potential collaborations and partnerships. The exchange of knowledge and expertise could benefit both parties and promote scientific advancements.  326 слів, але може іноземні партнери щось закритикують.. А ні, самі викинемо  Наслідки агресії:   1. Завгородній О. 2. Перебої з електропостачанням 3. Неможливість повноцінних наукових досліджень через повітряні тривоги 4. Неповна зайнятість 5. Пошкодження корпусу ФФ 6. Неможливість виїзду за кордон для участі в конференціях та обміну досвідом 7. Зменшення кількості внутрішніх конференцій   Ongoing Russia's war of aggression is greatly impacting our scientific research and development work. With frequent power outages, it is becoming increasingly challenging to conduct experiments and carry out long-term calculations, resulting in project delays and missed deadlines. Besides, the constant air raids and the need to take cover impede our scientific research efforts, causing significant roadblocks in the progress of our investigations. We often have to adjust our work schedules according to risks, which reduces the efficiency of our research. Furthermore, the ongoing conflict in Ukraine has resulted in a substantial reduction in researchers' salaries. With only 60 to 75 percent of their regular pay, scientists are losing motivation in their work, leading to decreased efforts in scientific research activities.  The frequent missile attacks have also caused damage to our faculty buildings, mostly damaging the windows. This damage might seem minor, but it is still limiting our abilities to carry out normal research work, particularly during the cold season. Travel restrictions placed on military scientists are also hindering the exchange of knowledge and insights with international partners. Additionally, the reduced number of local conferences is causing a sense of isolation and limited collaborations among domestic researchers.  One of our team members (Oleksii Zavhorodnii) used to live in Volnovakha, a city located 70 km away from Donetsk, before the war broke out. When the conflict began, the city was surrounded, and due to constant artillery shelling, he and his family were forced to take shelter in a basement for over a week. Eventually, they could evacuate through the only road controlled by the Ukrainian Armed Forces, which was continually targeted by the occupiers with various forms of artillery. Later, he found out that his home had been completely destroyed due to shelling. Presently, the city of Volnovakha remains occupied.  In conclusion, Russian aggression is having a significant adverse impact on our scientific research and development efforts, harming our nation's scientific and economic progress. It is important that we take proactive measures to mitigate these effects and continue our work to push back against the challenges presented by the war.  Як перше наближення... про Завгороднього пізніше  Чудово, аж сам просльозився! Краще б рука до гаманця потягнулася  Потрібно ще буде підготувати Brief outline of the research project (abstract) - до 250 слів  **Один з учасників нашої команди () перед початком війни жив у місті Волноваха, що за 70 км від Донецька. На початку агресії місто було оточене. Через постійні артилерійські обстріли він зі своєю сім’єю більше тижня жив у підвалі. Евакуюватися вдалося по єдиній дорозі, яка була під контролем ЗСУ, проте обстрілювалася окупантами з усіх видів гармат. Через деякий час він дізнався, що його житло повністю зруйноване в результаті обстрілів. На сьогодні місто Волноваха залишається в окупації.**  **One of our team members used to live in Volnovakha, a city located 70 km away from Donetsk before the war broke out. When the conflict began, the city was surrounded, and due to constant artillery shelling, he and his family were forced to take shelter in a basement for over a week. Eventually, they could evacuate through the only road controlled by the Ukrainian Armed Forces, which was continually targeted by the occupiers with various forms of artillery. Later, he found out that his home had been completely destroyed due to shelling. Presently, the city of Volnovakha remains occupied.**  **Війну я зустрів, перебуваючи в місті Волноваха, що за 70 км від Донецька. Розділений із сім'єю на початку війни, намагався разом зі своїми сусідами по вулиці, на простреленому осколками мікроавтобусі своїх сусідів, виїхати з кільця, яке на той час вже встигли створити окупанти навколо мого міста. Єдина дорога, яка була під контролем ЗСУ і давала можливість виїхати з міста - обстрілювалася окупантами з усіх видів гармат. Тож залишалося тільки проїхати на повній швидкості цю "дорогу життя" і сподіватися на краще. На цьому мосту, який нависав над залізницею, було безліч машин, які так і не виїхали з кільця, навіть за наявності білих прапорів, що стирчали з їхніх вікон, ці люди вже назавжди залишаться у Волновасі. Покинувши місто, ми приїхали у Велику Новосілку, дорогою зупиняючись біля прикордонних сіл, щоб набрати в мікроавтобус людей, у яких не було можливості евакуюватися своїми силами. У місті ми з моїми сусідами розділилися: я шукав способи витягнути сім'ю з Волновахи (мої батьки не хотіли залишати дім і тварин) і залишився у знайомих сестри, а мої сусіди тримали шлях на захід України. У момент, коли було ухвалено рішення про припинення вогню обома сторонами, щоб люди нарешті без затримок могли виїхати з міста, мої батьки скористалися моментів і за допомогою волонтерів змогли виїхати. Коли мої батьки приїхали до мене, фронт дійшов і до Великої Новосілки. Ми одразу ж покинули місто і поїхали евакуаційним автобусом до Покровська, де сіли на поїзд до Львова. У Волновасі ми всією сім'єю сиділи тижні в підвалі, товщина стелі якого була 1 шлакоблок, він міг врятувати нас тільки від осколків. Моє рішення виїхати з міста підштовхнув ранковий обстріл окупантами мого провулка. Майже всім сусідам того ранку знищило будинки. Через те, що я живу в низькому будинку, в нього снаряди так і не попали. Проте, вже коли ми їхали до Львова, нам передали люди, які виїжджали пізніше за моїх батьків, що хати більше немає, як і провулка.** |

**2.3.3 Dissemination of the results\*.** *(Max 200 words)*

Please describe how you plan or would like to disseminate the results of the research project.

|  |
| --- |
| Disseminating the results of the research is crucial for maximizing the impact of the project. Here are some ways in which we plan to disseminate the results of the research project:   1. Conference Presentations: We plan to present the results of the research project at least three relevant conferences in the fields of materials science, semiconductor engineering, solar cell technology, and thermal management. This will provide an opportunity to share the findings of the research with a wider audience and receive feedback from experts in the field. 2. Journal Publications: Based on the results of the research project, we plan to prepare at least 4 articles for publication in Scopus-indexed peer-reviewed journals. This will ensure that the findings are widely disseminated to the scientific community and can be cited by other researchers. 3. Social Media: We plan to use social media platforms such as Facebook, Instagram, or Telegram to disseminate the research findings to a wider audience. We will create posts and updates highlighting the key findings of the research and share links to the conference presentations and journal publications. |

**2.3.4 Possible references related to the research proposal (optional) .** *(Max 300 words)*

Citations used in the proposal text have to be listed here. References should be consecutively numbered using the format:

*[1] A. Author, B. Author, and C. Author, Title, Phys. Rev. B 50, pages (year). (DOI as hyperlink, if applicable)*

|  |
| --- |
| *[1] X. Qian, R. Yang, Machine learning for predicting thermal transport properties of solids, Materials Science & Engineering R 146, 100642 (2021) (*[*https://doi.org/10.1016/j.mser.2021.100642*](https://doi.org/10.1016/j.mser.2021.100642)*)*  *[2] K. Xu, T. Liang, Y. Fu et al., Gradient nano-grained graphene as 2D thermal rectifier: A molecular dynamics based machine learning study, Appl. Phys. Lett. 121, 133501 (2022) (*[*https://doi.org/10.1063/5.0108746*](https://doi.org/10.1063/5.0108746)*)*  *[3] Y. Yang, Y. Zhao, and L. Zhang Machine learning boosting the discovery of porous metamaterials with an abnormal thermal transport property, Appl. Phys. Lett. 122, 144102 (2023) (*[*https://doi.org/10.1063/5.0137665*](https://doi.org/10.1063/5.0137665_)*)*  *[4] R. Kurchin, J. Poindexter, V. Vahanissi et al., How much physics is in a current-voltage curve? Inferring defect properties from photovoltaic device measurements, IEEE J. Photovolt 10, 1532-1537 (2020). (*[*https://doi.org/10.1109/JPHOTOV.2020.3010105*](https://doi.org/10.1109/JPHOTOV.2020.3010105)*)*  *[5] S. Bulyarskiy, A. Lakalin, M. Saurov, and G. Gusarov, The effect of vacancy-impurity complexes in silicon on the current–voltage characteristics of p–n junctions, J Appl. Phys. 128, 155702 (2020). (*[*https://doi.org/10.1063/5.0023411*](https://doi.org/10.1063/5.0023411)*)*  *[6] Y. Buratti, J. Dick, Q. Gia, and Z. Hameiri, Deep Learning Extraction of the Temperature-Dependent Parameters of Bulk Defect, ACS Appl. Mater. Interfaces 14, 48647-48657 (2022). (*[*https://doi.org/10.1021/acsami.2c12162*](https://doi.org/10.1021/acsami.2c12162)*)*  *[7] O. Olikh, O. Lozitsky, and O. Zavhorodnii, Estimation for iron contamination in Si solar cell by ideality factor: Deep neural network approach, Prog. Photovolt. Res. Appl. 30, 648-660 (2022).(<https://doi.org/10.1002/pip.3539>)* |

**2.4 RESEARCH TEAM DESCRIPTION and FINANCIAL PLAN**

**2.4.1 Description of the roles within the research team\*.** *(Max 500 words)*

Please describe what are the roles, availabilities and tasks of each of the research team members within the research project. *Please note that the qualification, expertise, effort and roles of the members within the research project must be in line with the financial plan of the team. Each team member should have a meaningful role in the project.*

|  |
| --- |
| The following are the roles, availabilities, and tasks of each team member:   1. Principal Investigator (Olikh Oleg): The PI is responsible for supervising the entire project and ensuring that it meets the objectives. He is also responsible for interacting with stakeholders, and managing the research team. The PI will be available full-time throughout the project's duration. His tasks include directing the project's overall strategy, developing the methodology of machine learning models using, and overseeing data collection and machine learning code writing*.* Additionally, he will develop a model for simulating solar cells, analyze the data, and review & editing scientific papers and reports. 2. Researcher: The researcher will be available full-time throughout the project's duration. He will have expertise in molecular dynamics modeling of thermal transport. His tasks include performing simulations, data collection, models development and contributing to publications and presentations. 3. Research Assistant: The research assistant will be full-time and will work closely with the principal investigator and researcher. His tasks include running experiments to measure the transport properties of silicon structures, assisting in manuscript preparation, and providing general support for the research team. 4. Graduate Student 1 (Oleksii Zavhorodnii): The graduate student 1 will be 75% working on the projectand will work closely with the principal investigator. His tasks include collecting and processing experimental data relating to solar cells, implementing and testing machine learning models, and contributing to the draft of papers and presentations. 5. Graduate Student 2: 6. Student: |

**2.4.2 Financial plan\*.** *(Max 500 words)*

Please describe how the team suggests to distribute the monthly grants within the team members. *Please kindly note that the monthly grant amount per each team member should reflect on his/her qualifications, years of experience, planned effort and role within the suggested research project[[4]](#footnote-5) [[5]](#footnote-6) [[6]](#footnote-7)*

|  |  |  |
| --- | --- | --- |
| **Please indicate for your research team what are the wished estimated monthly grants per each member** *(within the maximum and minimum amounts described in the ToR ):* | | |
| ***Role*** | ***Name and Surname (English)*** | ***Euro per Month*** |
| **PI:** |  | *Min 700 Max 1,600* |
| **Team Member 2:** |  |  |
| **Team Member 3:** |  |  |
| **Team Member 4:** |  |  |
| **Team Member 5:** |  |  |
|  |  |  |

*If your team is composed by more than 5 Members please add new table lines.*

**2.4.3 Research team members information**

The information of the Principal Investigator (considered as Team Member 1) is already included in the online application form, no need to repeat them here.

**Team Member 2 – information**

|  |  |
| --- | --- |
| **First name ENG[[7]](#footnote-8)\*** |  |
| **Family name ENG\*** |  |
| **Date of Birth\*** | *Dd/mm/yyy* |
| **Gender\*** | *M / F / Non-binary* |
| **Phone number(s)** |  |
| **E-mail address(es)\*** |  |
| **Institute of affiliation[[8]](#footnote-9)\*** |  |
| **Affiliation Institute address** | *Street name and street number, city, postal address, country* |
| **Current position[[9]](#footnote-10)\*** |  |
| **Country of permanent residence\*** |  |
| **Country of current residence\*** | *Only if different from permanent residence. In case you live in a different country now, please specify since when.* |
| **Citizenship** |  |
| **Knowledge of English \*** | *Please select between:*  *Excellent – Very good – Good – Fair - Basic* |
| **Highest level of instruction achieved\*** | *e.g. PhD, Master, Bachelor in …(please specify the field)* |

**Team Member 3 – information**

|  |  |
| --- | --- |
| **First name ENG[[10]](#footnote-11)\*** | Vasyl |
| **Family name ENG\*** | Kuryliuk |
| **Date of Birth\*** | *23/07/1982* |
| **Gender\*** | *M* |
| **Phone number(s)** |  |
| **E-mail address(es)\*** | *kuryliuk@knu.ua* |
| **Institute of affiliation[[11]](#footnote-12)\*** | *Taras Shevchenko National University of Kyiv* |
| **Affiliation Institute address** | *Street name and street number, city, postal address, country*  *Volodymyrska Street 64/13, Kyiv, 01601, Ukraine* |
| **Current position[[12]](#footnote-13)\*** | *Head of Department of Metal Physics* |
| **Country of permanent residence\*** | *Ukraine* |
| **Country of current residence\*** |  |
| **Citizenship** | *Ukraine* |
| **Knowledge of English \*** | *Good* |
| **Highest level of instruction achieved\*** | *PhD in Solid State Physics* |

**Team Member 4 – information**

|  |  |
| --- | --- |
| **First name ENG[[13]](#footnote-14)\*** |  |
| **Family name ENG\*** |  |
| **Date of birth\*** | *Dd/mm/yyyy* |
| **Gender\*** | *M / F / Non-binary* |
| **Phone number(s)** |  |
| **E-mail address(es)\*** |  |
| **Institute of affiliation[[14]](#footnote-15)\*** |  |
| **Affiliation Institute address** | *Street name and street number, city, postal address, country* |
| **Current position[[15]](#footnote-16)\*** |  |
| **Country of permanent residence\*** |  |
| **Country of current residence\*** | *Only if different from permanent residence. In case you live in a different country now, please specify since when.* |
| **Citizenship** |  |
| **Knowledge of English \*** | *Please select between:*  *Excellent – Very good – Good – Fair - Basic* |
| **Highest level of instruction achieved\*** | *e.g. PhD, Master, Bachelor in …(please specify the field)* |

**Team Member 5 – information**

|  |  |
| --- | --- |
| **First name ENG[[16]](#footnote-17)\*** |  |
| **Family name ENG\*** |  |
| **Date of birth\*** | *Dd/mm/yyyy* |
| **Gender\*** | *M / F / Non-binary* |
| **Phone number(s)** |  |
| **E-mail address(es)\*** |  |
| **Institute of affiliation[[17]](#footnote-18)\*** |  |
| **Affiliation Institute address** | *Street name and street number, city, postal address, country* |
| **Current position[[18]](#footnote-19)\*** |  |
| **Country of permanent residence\*** |  |
| **Country of current residence\*** | *Only if different from permanent residence. In case you live in a different country now, please specify since when.* |
| **Citizenship** |  |
| **Knowledge of English \*** | *Please select between:*  *Excellent – Very good – Good – Fair - Basic* |
| **Highest level of instruction achieved\*** | *e.g. PhD, Master, Bachelor in …(please specify the field)* |

**Team Member 6 – information**

|  |  |
| --- | --- |
| **First name ENG[[19]](#footnote-20)\*** |  |
| **Family name ENG\*** |  |
| **Date of birth\*** | *Dd/mm/yyyy* |
| **Gender\*** | *M / F / Non-binary* |
| **Phone number(s)** |  |
| **E-mail address(es)\*** |  |
| **Institute of affiliation[[20]](#footnote-21)\*** |  |
| **Affiliation Institute address** | *Street name and street number, city, postal address, country* |
| **Current position[[21]](#footnote-22)\*** |  |
| **Country of permanent residence\*** |  |
| **Country of current residence\*** | *Only if different from permanent residence. In case you live in a different country now, please specify since when.* |
| **Citizenship** |  |
| **Knowledge of English \*** | *Please select between:*  *Excellent – Very good – Good – Fair - Basic* |
| **Highest level of instruction achieved\*** | *e.g. PhD, Master, Bachelor in …(please specify the field)* |

***If you wish to add more team Members, please copy this table, paste it below and add the details of the additional team member(s).***

**2.5 SIGNATURES**

***After completing all the chapters of this form, it shall be signed by the PI and by all research team members, then the PI should upload it together with all other relevant documents (indicated in the Terms of Reference of the call) in the online application form.***

***Please remember that the limit in the number of words per each section of the application form constitutes one of the eligibility criteria, so make sure that all requirements are respected.***

***Disclaimer on Intellectual Property Rights and Copyright****: A proposal for the EURIZON Fellowship programme must respect the fundamental ethical principles for scientific research. EURIZON Secretariat condemns the replication of ideas, data, results without due permission and acknowledgement. Please make sure that the ideas developed in this research proposal are yours (and/or of the people mentioned in the paragraph 2 “Research team”) and that you own or have received the necessary authorizations from the intellectual property rights holders to validly use data and materials that you include in the Application form.*

***Privacy Notice***

*Please, be informed: when applying for the EURIZON Remote Research Grant Fellowship, you agree that the personal data and documents that you provide to the EURIZON Secretariat and Review Panel will be stored and processed for the purpose of participating in the EURIZON Remote Research Grant application procedure. The personal data and documents from all applicants will be stored and processed according to DESY data privacy policy :* [*https://www.desy.de/data\_privacy\_policy/index\_eng.html*](https://www.desy.de/data_privacy_policy/index_eng.html)

***Signature of the PI: Date:*** *dd/mm/yyyy*

***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_***

***Signatures of all other team members:***

***Name, Family name(English) Signature***

***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_***

***Name, Family name(English) Signature***

***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_***

***Name, Family name(English) Signature***

***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_***

***Name, Family name(English) Signature***

***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*** ***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_***

***Name, Family name(English)***  ***Signature***

***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*** ***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_***

***Please note that this document must be signed by all team members, so if your team is composed by more than 5 members, please add their signatures here below.***

1. Please verify that this information corresponds to the one reported in section 1 of the online application form. [↑](#footnote-ref-2)
2. Please verify this information corresponds to the one reported in the section 4 of the online application form. [↑](#footnote-ref-3)
3. The name and contact details of the European partners are to be mentioned in the Application form (Section 3). [↑](#footnote-ref-4)
4. Each team member will receive a constant amount of monthly grant during the whole duration of the fellowship. [↑](#footnote-ref-5)
5. Candidates that are not in a vulnerable condition or that are already beneficiaries of other support grants/ fellowships (above 1,000 Euro) can participate in the programme but are not entitled to receive the monthly grant. [↑](#footnote-ref-6)
6. Teams should be composed by 2-5 Members (including the PI). Teams can include more than 5 Members, but the maximum monthly grant available for the research project will not exceed 6,500 Euro. [↑](#footnote-ref-7)
7. As mentioned in the ID document, please use English alphabet; [↑](#footnote-ref-8)
8. Please mention if you are still affiliated to that institute or until when you were affiliated; [↑](#footnote-ref-9)
9. Please mention if you are still in the same position or until when you held it; [↑](#footnote-ref-10)
10. As mentioned in the ID document, please use English alphabet; [↑](#footnote-ref-11)
11. Please mention if you are still affiliated to that institute or until when you were affiliated; [↑](#footnote-ref-12)
12. Please mention if you are still in the same position or until when you held it; [↑](#footnote-ref-13)
13. As mentioned in the ID document, please use English alphabet; [↑](#footnote-ref-14)
14. Please mention if you are still affiliated to that institute or until when you were affiliated; [↑](#footnote-ref-15)
15. Please mention if you are still in the same position or until when you held it; [↑](#footnote-ref-16)
16. As mentioned in the ID document, please use English alphabet; [↑](#footnote-ref-17)
17. Please mention if you are still affiliated to that institute or until when you were affiliated; [↑](#footnote-ref-18)
18. Please mention if you are still in the same position or until when you held it; [↑](#footnote-ref-19)
19. As mentioned in the ID document, please use English alphabet; [↑](#footnote-ref-20)
20. Please mention if you are still affiliated to that institute or until when you were affiliated; [↑](#footnote-ref-21)
21. Please mention if you are still in the same position or until when you held it; [↑](#footnote-ref-22)