## Gant Chart
Da: includes deliverables 1.1.1 to 1.1.9. Db: Includes deliverables 1.1.10 to D.1.3: Congresses NOVA-Bioscope. D2.2: Boot Camps. Expected datas for simultaneous launching. Each delivery means 8 boots camps). D4.1 Reporting every 6 months. D.4.2 Project meetings.
|  | SMART | TASK DESCRIPTION |  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
WP1 Foundation and implementation (2026-2028????): Coordinator: NOVA
|  | T1.1 | Dr. Vida Digital Transformation | NOVA | 2026 9: M1.a; 2026 12: M1.b; 2027 15: Da; 2027 21: Db
|  | T1.2 | Learning Outcomes | YAGMA | 2027 15: M1.2; 2028 27: D1.2
|  | T1.3 | Start Up SMART UP | NOVA | 2027 22: M1.3; 2028 30: D1.3
WP2 - 1st Expansion and Global Impact (2028-2030): Coordinator UPE (Replacement: UNIBO)
|  | T2.1 | 1st Expansion and Global Impact | UPE (UNIBO) | 2027 24: M2.1; 2028 36: D2.1
|  | T2.2 | Web-Based Tools | YAGMA | 2027 23: M2.2; 2028 28: D2.3
|  | T2.3 | Boot Camps | NOVA | 2027 19: D2.3; 2028 25: D2.3; 2028 32: D2.3; 2028 34: M2.3; 2029 37: D2.3; 2029 43: D2.3; 2030 49: D2.3
|  | T.2.4 | 2nd Expansion | UNIBO | 2029 46: M2.4; 2030 60: D2.4
WP3 Dissemination, outreach and exploitation (2026-2030): Coordinator: EXELISIS
| EXELIXIS | T3.1 | Dissemination | EXELISIS | 2026 6: D3.1
|  | T3.2 | Communication | EXELISIS | 2026 8: M3.2.1; 2026 9: M3.2.2; 2026 12: M3.2.3; 2027 14: M3.2.4; 2027 22: M3.2.5; 2028 32: M3.2.6; 2029 44: M3.2.7; 2030 50: M3.2.8; 2030 58: D3.2
|  | T3.3 | Exploitation | EXELISIS | 2026 2: M3.3.1; 2026 5: M3.3.2; 2026 7: D.3.3; 2026 8: M3.3.3; 2027 17: M3.3.4; 2028 29: M3.3.5; 2029 47: M3.3.6
WP4 Project and IPR Management (2026-2030): Coordinator NOVA
|  | T4.1 | Dayly Management | NOVA | 2026 2: M4.1.1; 2026 5: D4.1.1; 2026 10: M4.1.2; 2026 11: D4.1.2; 2027 17: D4.1.1; 2027 23: D4.1.2; 2028 28: M4.1.3; 2028 29: D4.1.1; 2028 35: D4.1.2; 2029 41: D4.1.1; 2029 47: D4.1.2; 2030 53: D4.1.1; 2030 56: M4.1.4; 2030 59: D4.1.2
|  | T4.2 | Project Meetings | NOVA | 2026 4: M4.2.2; 2026 5: M4.2.1; 2026 8: D4.2; 2026 10: M4.2.2; 2026 11: D4.2; 2027 17: D4.2; 2027 22: M4.2.2; 2027 23: D4.2; 2028 29: D4.2; 2028 34: M4.2.2; 2028 35: D4.2; 2029 41: D4.2; 2029 46: M4.2.2; 2029 47: D4.2; 2030 53: D4.2; 2030 56: M4.2.2; 2030 58: M4.2.3; 2030 59: D4.2
|  | T4.3 | Consortium Agreement | NOVA | 2026 2: M.4.3.1; 2026 4: D.4.3
W6 Scientific research. (2027-2030): Coordinator STABV
|  | T5.1 | CMV and ZICA New Primers | STABV | 2026 9: M5.1; 2027 15: D.5.1
|  | T5.4 | Implementation of Regulations | STABV | 2027 18: M5.2.1; 2027 19: M5.2.2; 2027 23: D5.2.1; 2027 24: D5.2.2
|  | T5.3 | Analytical Validation | STABV | 2028 27: M5.3; 2029 38: D5.3
|  | T5.4 | Regulatoru+Market Paperwork | STABV | 2029 44: M5.4.1; 2029 45: M5.4.2; 2030 49: D5.4.1; 2030 50: D.5.4.2
|  | T5.5 | Calibration Algorithms | KNU | 2027 18: M6.5.1; 2027 23: M5.5.2; 2027 24: D5.5.1; 2028 36: D5.5.2
|  | T5.6 | Calibration Validation | KNU | 2028 35: M5.6.1; 2029 38: M5.6.2; 2029 41: D5.6.1; 2029 47: D5.6.2

## Sheet2
| TASK TITLE | NOVA | UNIBO | HUJI | STABV | UOA | EXELISIS | YAGMA | UPE | KNU | UHU | UNICAMP
T1.1 | Dr. Vida Digital Transformation | Develop CM Virus (1) and Leads T1.1 | Develop Bacteria Identification (2) | Develop Myeloma (3) | Develop Zica Virus (4) | Bioinformatics (ALL) (5) |  | questionaries, Statistics, AI (6) | Develop Kidney (7) | Develop lactosa (8) | Develop As (9) | Develop Hg (10)
T1.2 | Learning Outcomes | Tester (2-10) | Tester (1,3-10) | Tester (1,2, 4-10) | Tester (1-3, 5-10) | Tester (1-4, 6-10) |  | Data Management (1-5, 7-10) and Leads T1.2 | Tester (1-6, 8-10) | Tester (1-7,9,10) | Tester (1-8, 10) | Tester (1-9)
T1.3 | Start Up SMART UP | Creation of Smart up and Leads T1.3 | Aids in development | Aids in development | Aids in development | Aids in development |  | Aids in development | Aids in development | Aids in development | Aids in development | Aids in development
T2.1 | 1st Expansion and Global Impact | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS |  | Engage 2 HEIS | Engage 2 HEIS and Leads T2.1 | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS
T2.2 | Web-Based Tools | Aids in development | Aids in development | Aids in development | Aids in development | Aids in development |  | Web based Tools. Coordiante T2.2 | Aids in development | Aids in development | Aids in development | Aids in development
T2.3 | Boot Camps | 2 boot camps annually. Leads T2.3 | 2 boot camps annually | 2 boot camps annually | 2 boot camps annually | 2 boot camps annually |  | 2 boot camps annually | 2 boot camps annually | 2 boot camps annually | 2 boot camps annually | 2 boot camps annually
T2.4 | 2nd Expansion | Engage 4 HEIS. Leads T.2.4 | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS |  | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS | Engage 2 HEIS
T3.1 | Dissemination | Aids Dissemination. Organizes 5-6 conferences yearly (www.bioscopegroup.org) | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly | Leads dissemination | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly | Aids Dissemination organizes 2 conferences yearly-Visit 2 conferences yearly
T3.2 | Communication | Aids Communication | Aids Communication | Aids Communication | Aids Communication | Aids Communication | Leads Communication | Aids Communication | Aids Communication | Aids Communication | Aids Communication | Aids Communication
T3.3 | Exploitation | Aids Exploitation | Aids Exploitation | Aids Exploitation | Aids Exploitation | Aids Exploitation | Leads Exploitation | Aids Exploitation | Aids Exploitation | Aids Exploitation | Aids Exploitation | Aids Exploitation
T4.1 | Dayly Management | Leads management and Leads T4.1 | Implement Coordinator strategy | Implement Coordinator strategy | Implement Coordinator strategy | Implement Coordinator strategy | Implement Coordinator strategy | Implement Coordinator strategy | Implement Coordinator strategy | Implement Coordinator strategy | Implement Coordinator strategy | Implement Coordinator strategy
T4.2 | Project Meetings | Leads Project meetings | Participate in meetings | Participate in meetings | Participate in meetings | Participate in meetings | Folows Consortium agreement | Participate in meetings | Participate in meetings | Participate in meetings | Participate in meetings | Participate in meetings
T4.3 | Consortium Agreement | Leads consortiium agreement | Folows Consortium agreement | Folows Consortium agreement | Folows Consortium agreement | Folows Consortium agreement | Folows Consortium agreement | Folows Consortium agreement | Folows Consortium agreement | Folows Consortium agreement | Folows Consortium agreement | Folows Consortium agreement
T5.1 | CMV and ZICA New Primers |  |  |  | Leads T5.1-In silico developemnt for CMV and ZICA primers | In silico Validation
T5.2 | Implementation of Regulations | Search national regulations | Search national regulations | Search national regulations | leads T5.2 Mapping ISSO requeriments | Search national regulations |  | Search national regulations | Search national regulations | Search national regulations | Search national regulations | Search national regulations
T5.3 | Analytical Validation | Analytical validation | Analytical validation | Analytical validation | Leads T5.3 Analytcal validation | Analytical validation |  | Analytical validation | Analytical validation | Analytical validation | Analytical validation | Analytical validation
T5.4 | Regulatory+Market Paperwork |  |  |  | Leads T.5.4 Regulatory submission
T5.5 | Calibration Algorithms | [8 empty] | Leads T5.4 Calibration kit
T5.6 | Calibration Validation | Aids in testing calibration kit | Aids in testing calibration kit | Aids in testing calibration kit | Aids in testing calibration kit | Aids in testing calibration kit |  | Aids in testing calibration kit | Aids in testing calibration kit | Leads Testing Calibration Kit | Leads Testing Calibration Kit | Leads Testing Calibration Kit
2 researchers (5 years)
Short Stays (5 days) twice a year, rotating to diferente labs to learn from the partners and toe xhangue experiences. (1000 airplane + 2500 Hotel + 500 food)*2*5= 40 000
20 Dr. Vida device to work with, 20 Dr Vida to share with othe HEIs
150 000 chemical reagents
20.000 for 40 computers
Support For organizing 5 conferences every year: total of 10 000*2*50 = 100 000
Travel to 2 conferences every year: (3 days): (1000+900+300)*2*5= 22000
Administrative staff explotaition office-Soft skills